## Timetable for website
Adult hospital inpatient experience survey
Phase | Process | Q4 Apr - Jun 22 | Q1 July - Sept 22 | Q2 Oct - Dec 22 | Q3 Jan - Mar 23 | Q4 Apr - Jun 23
Sample | Survey period reminder | 2022-04-08 | 2022-07-04 | 2022-10-04 | 2023-02-07 | 2023-05-02
Sample | Inpatients discharged from DHB for set 4-week period | 11 April–8 May 2022 | 5 July–1 August 2022 | 5 October–4 November 2022 | 8 February–7 March 2023 | 6 April–4 May 2023
Sample | Inpatients discharged from DHB for set 2-week period | 25 April–8 May 2022 | 19 July–1 August 2022 | 19 October–4 November 2022 | 22 February–7 March 2023 | 20 April–4 May 2023
Sample | DHB file upload ready for trial/testing | 2022-05-10 | 2022-08-02 | 2022-11-08 | 2023-03-08 | 2023-05-09
Sample | DHB extracts patient data | 2022-05-17 | 2022-08-09 | 2022-11-15 | 2023-03-15 | 2023-05-16
Sample | Extract uploaded to national survey provider | 2022-05-17 | 2022-08-09 | 2022-11-15 | 2023-03-15 | 2023-05-16
Fieldwork | Survey emailed or texted to sample group of patients | 2022-05-17 | 2022-08-10 | 2022-11-16 | 2023-03-16 | 2023-05-17
Fieldwork | Survey posted to patients | 2022-05-18 | 2022-08-11 | 2022-11-17 | 2023-03-17 | 2023-05-18
Fieldwork | Reminder (email/text) sent 7 days later | 2022-05-24 | 2022-08-17 | 2022-11-23 | 2023-03-23 | 2023-05-23
Fieldwork | File for post reminders available by 10 am | 2022-05-27 | 2022-08-20 | 2022-11-26 | 2023-03-26 | 2023-05-26
Fieldwork | Reminder (post) sent 10 days later | 2022-05-27 | 2022-08-20 | 2022-11-26 | 2023-03-26 | 2023-05-26
Fieldwork | Email/text survey links close after 21 days | 2022-06-07 | 2022-08-31 | 2022-12-07 | 2023-04-06 | 2023-06-07
Fieldwork | All paper survey links close (DHBs enter data in national database by...) | 2022-06-29 | 2022-09-21 | 2023-01-05 | 2023-04-27 | 2023-06-28
Reporting | Survey results posted to sector secure online portal | 2022-07-05 | 2022-09-27 | 2023-01-11 | 2023-05-03 | 2023-07-04
Reporting | Weighted survey results published on Experience Explorer | 2022-07-29 | 2022-10-21 | 2022-02-04 | 2023-05-26 | 2023-07-28
Formulas:
Q1 July - Sept 22 = [Q1 July - Sept 22, row below]-7
Q1 July - Sept 22 = [Q1 July - Sept 22, row above]+1
Q4 Apr - Jun 23 = [Q4 Apr - Jun 23, row above]+1
Q2 Oct - Dec 22 = [Q2 Oct - Dec 22, row above]+6