## Sheet1
HCSS 2025
Phase | Process | Guide | Date | Date
Data specification | Data specification finalised |  | 10 July 2024
Data specification | Providers to run test extract to confirm pre-fieldwork |  | 12-23 August 2024
Questionnaire | Questionnaire finalised and signed-off |  | Week of 22 July
Privacy | Providers confirm privacy obligations are met | Complete by | Monday 5 August 2024 | 2025-05-05
Notifications | Pre-notification flyers, information for support workers, website and newsletter content for providers | Available by | Monday 12 August 2024 | 2025-05-12
Notifications | Providers share materials | 1 week prior to survey sample weeks | Monday 12 August 2024 | 2025-05-12
Sampling | Survey sample weeks People with a ‘last visit date’ at the provider in the 4-week sample period | Start Monday | Monday, 19 August 2024 | 2025-05-19
Sampling |  | End Sunday | Sunday, 15 September 2024 | 2025-06-15
Sampling | Providers extract client data and upload to Ipsos portal | During week following end of survey sample period | 16-20 September 2024 | 16-20 June 2025
Fieldwork | Launch of survey: email invitation sent Response rate becomes available on data collection portal |  | 2024-09-23 | 2025-06-24
Fieldwork | Comment moderation and contact request review period begins | 1 day following email invite | 2024-09-24 | 2025-06-25
Fieldwork | SMS reminder sent (Two days following email invitation) | 2 days following email invite | 2024-09-25 | 2025-06-27
Fieldwork | Email reminder sent (seven days following email invitation) | 7 days following email invite | 2024-09-30 | 2025-07-01
Fieldwork | Decision on hard copy survey | 9 days following email invite | 2024-10-02 | 2025-07-03
Fieldwork | Email / text survey links close (21 days following launch of survey) | 21 days following launch | 2024-10-13 | 2025-07-15
Fieldwork | Hard copy survey close | 28 days following sending | 2024-10-30 | 2025-07-30
Reporting | Survey results | To be confirmed
Formulas:
Date = [Date, row below]-7
Date = [Date, row above]+2