## AHS-I
| Adult hospital inpatient experience survey |  | Q4 May 2025 | Q1 August 2025 | Q2 November 2025 | Q3 February 2026 | Q4 May 2026
Phase | Process | Guide | Q4 Apr - Jun 25 | Q1 July - Sept 25 | Q2 Oct - Dec 25 | Q3 Jan - Mar 26 | Q4 Apr - Jun 26
Wave set-up | Survey sample weeks reminder | Friday before survey week | 2025-04-04 | 2025-06-27 | 2025-09-19 | 2026-01-09 | 2026-04-02
Sampling | Survey sample weeks (4 weeks): Dates of inpatients discharged from hospital | Monday-Sunday (4 weeks) | 7 April-4 May 2025 | 30 June - 27 July 2025 | 22 September - 19 October 2025 | 12 January - 8 February 2026 | 6 April-3 May 2026
Sampling | Survey sample weeks (2 weeks): Dates of inpatients discharged from hospital | Monday-Sunday (2 weeks) | 21 April-4 May 2025 | 14 July - 27 July 2025 | 6 - 19 October 2025 | 26 January - 8 February 2026 | 20 April-3 May 2026
Sampling | Batch open - districts can start uploading patient sample files | Tuesday after survey sample weeks | 2025-05-06 | 2025-07-29 | 2025-10-21 | 2026-02-10 | 2026-05-05
Sampling | District patient sample file upload deadline | 6 days after batch opening 1 day before to launch of AHS-I | 2025-05-12 | 2025-08-04 | 2025-10-24 | 2026-02-16 | 2026-05-11
Fieldwork | Launch of survey: email invitation sent to sample group of patients - Response rate becomes available on data collection portal | 7 days after batch opening 1 week before launch of APCS (to stagger the invitation process) | 2025-05-13 | 2025-08-05 | 2025-10-28 | 2026-02-17 | 2026-05-12
Fieldwork | SMS reminder & invitation sent to sample group of patients (2 days following initial email invite) | 2 days after email invite | 2025-05-15 | 2025-08-07 | 2025-10-30 | 2026-02-19 | 2026-05-14
Fieldwork | Email reminder sent (7 days following initial email invite) | 7 days after invite | 2025-05-20 | 2025-08-12 | 2025-11-04 | 2026-02-24 | 2026-05-19
Fieldwork | Email/text survey links close (21 days following launch of survey) | 21 days after launch | 2025-06-03 | 2025-08-26 | 2025-11-18 | 2026-03-10 | 2026-06-02
Reporting | Survey results posted to sector secure online reporting portal | 7 days after survey close | 2025-06-10 | 2025-09-02 | 2025-11-25 | 2026-03-17 | 2026-06-09
Reporting | Results published on Experience Explorer |  | Friday, 29 August 2025 | Friday, 28 November 2025 | 2026-02-27 | 2026-05-29 | 2026-08-28
Formulas:
Q4 May 2025 = [Q4 May 2025, row above]+2
Q1 August 2025 = [Q1 August 2025, row above]+2
Q2 November 2025 = [Q2 November 2025, row above]+2
Q3 February 2026 = [Q3 February 2026, row above]+2
Q4 May 2026 = [Q4 May 2026, row above]+2

## AHS-O
| Adult hospital outpatient experience survey |  | Q4 May 2025 | Q1 August 2025 | Q2 November 2025 | Q3 February 2026 | Q4 May 2026
Phase | Process | Guide 2-WEEK GAP FROM AHS-I | Q4 Apr - Jun 25 | Q1 July - Sept 25 | Q2 Oct - Dec 25 | Q3 Jan - Mar 26 | Q4 Apr - Jun 26
Wave set-up | Survey sample weeks reminder | Friday before survey sample weeks | 2025-05-16 | 2025-08-08 | 2025-10-31 | 2026-02-20 | 2026-05-15
Sampling | Survey sample weeks (2 weeks): Dates of appointment | Monday-Sunday (2 weeks) | 19 May - 1 June | 11-24 August 2025 | 3-16 November 2025 | 23 February-8 March 2026 | 18-31 May 2026
Sampling | Batch open - districts can start uploading patient sample files | Tuesday after survey sample weeks | 2025-06-03 | 2025-08-26 | 2025-11-18 | 2026-03-10 | 2026-06-02
Sampling | District patient sample file upload deadline | 6 days after batch opening 1 day before to launch of AHS-O | 2025-06-09 | 2025-09-01 | 2025-11-24 | 2026-03-16 | 2026-06-08
Fieldwork | Launch of survey: email invitation sent to sample group of patients - Response rate becomes available on data collection portal | 7 days after batch opening 1 day before launch of APCS (to stagger the invitation process) | 2025-06-10 | 2025-09-02 | 2025-11-25 | 2026-03-17 | 2026-06-09
Fieldwork | SMS reminder & invitation sent to sample group of patients (2 days following initial email invite) | 2 days after email invite | 2025-06-12 | 2025-09-04 | 2025-11-27 | 2026-03-19 | 2026-06-11
Fieldwork | Email reminder sent (7 days following initial email invite) | 7 days after invite | 2025-06-17 | 2025-09-09 | 2025-12-02 | 2026-03-24 | 2026-06-16
Fieldwork | Survey links close (21 days following launch of survey) | 21 days after launch | 2025-07-01 | 2025-09-23 | 2025-12-16 | 2026-04-07 | 2026-06-30
Reporting | Survey results available in raw data export from data collection portal | 7 days after survey close | 2025-07-08 | 2025-09-30 | 2025-12-23 | 2026-04-14 | 2026-07-07
Reporting | Results published on Experience Explorer |  | Friday, 29 August 2025 | 2025-11-28 | 2026-02-27 | 2026-05-29 | 2026-08-28
Formulas:
Q4 May 2025 = [Q4 May 2025, row above]+6
Q2 November 2025 = [Q2 November 2025, row above]+6
Q3 February 2026 = [Q3 February 2026, row above]+6
Q4 May 2026 = [Q4 May 2026, row above]+6
Q1 August 2025 = [Q1 August 2025, row above]+1

## APCS
| Adult primary care patient experience survey |  | Q4 May 2025 | Q1 August 2025 | Q2 November 2025 | Q3 February 2026 | Q4 May 2026
Phase | Process | Guide | Q4 Apr - Jun 25 | Q1 July - Sept 25 | Q2 Oct - Dec 25 | Q3 Jan - Mar 26 | Q4 Apr - Jun 26
Wave set-up | Facility ID file provided by the Ministry | 1 month prior to survey sample weeks | 2025-04-04 | 2025-06-27 | 2025-10-03 | 2026-01-09 | 2026-04-02
Wave set-up | Practice inclusion phase starts |  | 2025-04-04 | 2025-06-27 | 2025-10-03 | 2026-01-09 | 2026-04-02
Wave set-up | Reminder 1 - Practice inclusion phase | 1 week after start | 2025-04-11 | 2025-07-04 | 2025-10-10 | 2026-01-16 | 2026-04-09
Wave set-up | Reminder 2 - Practice inclusion phase | 2 weeks after start | 2025-04-18 | 2025-07-11 | 2025-10-17 | 2026-01-23 | 2026-04-16
Wave set-up | Reminder 3 - Practice inclusion phase | 3 weeks after start sent at 9am | 2025-04-25 | 2025-07-18 | 2025-10-24 | 2026-01-30 | 2026-04-23
Wave set-up | Deadline for PHOs to send participating practice information | 3 weeks after start 5pm deadline date | 2025-04-25 | 2025-07-18 | 2025-10-24 | 2026-01-30 | 2026-04-23
Wave set-up | Brochures and materials sent to practices by PHOs ahead of survey week | 1 week prior to survey sample weeks | 2025-04-28 | 2025-07-21 | 2025-10-28 | 2026-02-02 | 2026-04-28
Sampling | Survey sample weeks reminder | Friday prior to survey sample weeks | 2025-05-02 | 2025-07-25 | 2025-10-31 | 2026-02-05 | 2026-05-01
Sampling | Survey sample weeks Patients with a 'date of last consultation' at the practice they're enrolled with, in a set 1-week sample period each quarter - Week 1 - Census of Māori and Pacific respondents only - Week 2 - Sample drawn from full patient pool | Start Monday | 2025-05-05 | 2025-07-28 | 2025-11-03 | 2026-02-09 | 2026-05-04
Sampling |  | End Sunday | 2025-05-18 | 2025-08-10 | 2025-11-16 | 2026-02-22 | 2026-05-17
Sampling | Ministry extracts patient data | Monday following end of survey sample weeks | 2025-05-19 | 2025-08-11 | 2025-11-17 | 2026-02-23 | 2026-05-18
Sampling | Commission prioritized SMS sample + extract uploaded to survey provider | 1 day prior to survey launch | 2025-05-20 | 2025-08-12 | 2025-11-18 | 2026-02-24 | 2026-05-19
Fieldwork | Launch of survey: email invitation sent to sample group of patients - Response rate becomes available on data collection portal | 1 week following launch of AHS (to stagger the invitation process) | 2025-05-21 | 2025-08-13 | 2025-11-19 | 2026-02-25 | 2026-05-20
Fieldwork | Comment moderation and contact request review period begins | 1 day following email invite | 2025-05-22 | 2025-08-14 | 2025-11-20 | 2026-02-26 | 2026-05-21
Fieldwork | SMS reminder to sample group of patients (2 days following email invitation) | 2 days following email invite | 2025-05-23 | 2025-08-15 | 2025-11-21 | 2026-02-27 | 2026-05-22
Fieldwork | Email reminder sent (7 days following email invitation) | 7 days following email invite | 2025-05-28 | 2025-08-20 | 2025-11-26 | 2026-03-04 | 2026-05-27
Fieldwork | Email/text survey links close (21 days following launch of survey) | 21 days following launch | 2025-06-11 | 2025-09-03 | 2025-12-10 | 2026-03-18 | 2026-06-10
Reporting | Survey results posted to sector secure online reporting portal | 7 days after survey close | 2025-06-18 | 2025-09-10 | 2025-12-17 | 2026-03-25 | 2026-06-17
Reporting | Results published on Experience Explorer |  | Friday, 29 August 2025 | 2025-11-28 | 2026-02-27 | 2026-05-29 | 2026-08-28
Formulas:
Q4 May 2025 = [Q4 May 2025, row above]
Q4 May 2025 = [Q4 May 2025, row above]+13
Q1 August 2025 = [Q1 August 2025, row above]
Q1 August 2025 = [Q1 August 2025, row above]+13
Q2 November 2025 = [Q2 November 2025, row above]
Q2 November 2025 = [Q2 November 2025, row above]+13
Q3 February 2026 = [Q3 February 2026, row above]
Q3 February 2026 = [Q3 February 2026, row above]+13
Q4 May 2026 = [Q4 May 2026, row above]
Q4 May 2026 = [Q4 May 2026, row above]+13

## HCSS
HCSS 2025
Phase | Process | Guide | 2024 | Date
Data specification | Data specification finalised |  | 10 July 2024
Data specification | Providers to run test extract to confirm pre-fieldwork |  | 12-23 August 2024
Questionnaire | Questionnaire finalised and signed-off |  | Week of 22 July
Privacy | Providers confirm privacy obligations are met | Complete by | Monday 5 August 2024 | 2025-05-05
Notifications | Pre-notification flyers, information for support workers, website and newsletter content for providers | Available by | Monday 12 August 2024 | 2025-05-12
Notifications | Providers share materials | 1 week prior to survey sample weeks | Monday 12 August 2024 | 2025-05-12
Sampling | Survey sample weeks People with a ‘last visit date’ at the provider in the 4-week sample period | Start Monday | Monday, 19 August 2024 | 2025-05-19
Sampling |  | End Sunday | Sunday, 15 September 2024 | 2025-06-15
Sampling | Providers extract client data and upload to Ipsos portal | During week following end of survey sample period | 16-20 September 2024 | 16-23 June 2025
Fieldwork | Launch of survey: email invitation sent Response rate becomes available on data collection portal |  | 2024-09-23 | 2025-06-24
Fieldwork | Comment moderation and contact request review period begins | 1 day following email invite | 2024-09-24 | 2025-06-25
Fieldwork | SMS reminder sent (Two days following email invitation) | 2 days following email invite | 2024-09-25 | 2025-06-26
Fieldwork | Email reminder sent (seven days following email invitation) | 7 days following email invite | 2024-09-30 | 2025-07-01
Fieldwork | Decision on hard copy survey | 9 days following email invite | 2024-10-02 | 2025-07-03
Fieldwork | Email / text survey links close (21 days following launch of survey) | 21 days following launch | 2024-10-13 | 2025-07-15
Fieldwork | Hard copy survey close Data entry needs to be complete by this date | 28 days following sending | 2024-10-30 | 2025-07-30
Reporting | Survey results | To be confirmed
Formulas:
Date = [Date, row below]-7