## APCS
| Adult primary care patient experience survey |  | Q4 May 2023 | Q1 August 2023 | Q2 November 2023 | Q3 February 2024 | Q4 May 2024
Phase | Process | Guide | Q4 Apr - Jun 23 | Q1 July - Sept 23 | Q2 Oct - Dec 23 | Q3 Jan - Mar 24 | Q4 Apr - Jun 24
Wave set-up | Facility ID file provided by the Ministry | 1 month prior to survey sample weeks | 2023-04-06 | 2023-06-30 | 2023-09-29 | 2024-01-19 | 2024-04-05
Wave set-up | Practice inclusion phase starts |  | 2023-04-06 | 2023-06-30 | 2023-09-29 | 2024-01-19 | 2024-04-05
Wave set-up | Reminder 1 - Practice inclusion phase | 1 week after start | 2023-04-14 | 2023-07-07 | 2023-10-06 | 2024-01-26 | 2024-04-12
Wave set-up | Reminder 2 - Practice inclusion phase | 2 weeks after start | 2023-04-21 | 2023-07-13 | 2023-10-13 | 2024-02-02 | 2024-04-19
Wave set-up | Reminder 3 - Practice inclusion phase | 3 weeks after start sent at 9am | 2023-04-28 | 2023-07-21 | 2023-10-20 | 2024-02-09 | 2024-04-26
Wave set-up | Deadline for PHOs to send participating practice information | 3 weeks after start 5pm deadline date | 2023-04-28 | 2023-07-21 | 2023-10-20 | 2024-02-09 | 2024-04-26
Wave set-up | Brochures and materials sent to practices by PHOs ahead of survey week | 1 week prior to survey sample weeks | 2023-04-24 | 2023-07-24 | 2023-10-24 | 2024-02-12 | 2024-04-29
Sampling | Survey sample weeks reminder | Friday prior to survey sample weeks | 2023-04-28 | 2023-07-28 | 2023-10-27 | 2024-02-09 | 2024-04-26
Sampling | Survey sample weeks Patients with a 'date of last consultation' at the practice they're enrolled with, in a set 1-week sample period each quarter - Week 1 - Census of Māori and Pacific respondents only - Week 2 - Sample drawn from full patient pool | Start Monday | 2023-05-01 | 2023-07-31 | 2023-10-30 | 2024-02-19 | 2024-05-06
Sampling |  | End Sunday | 2023-05-14 | 2023-08-13 | 2023-11-12 | 2024-03-03 | 2024-05-19
Sampling | Ministry extracts patient data | Monday following end of survey sample weeks | 2023-05-15 | 2023-08-14 | 2023-11-13 | 2024-03-04 | 2024-05-20
Sampling | Commission prioritized SMS sample + extract uploaded to survey provider | 1 day prior to survey launch | 2023-05-16 | 2023-08-15 | 2023-11-14 | 2024-03-05 | 2024-05-21
Fieldwork | Launch of survey: email invitation sent to sample group of patients - Response rate available on portal | 1 week following launch of AHS (to stagger the invitation process) | 2023-05-17 | 2023-08-16 | 2023-11-15 | 2024-03-06 | 2024-05-22
Fieldwork | Comment moderation and contact request review period begins | 1 day following email invite | 2023-05-18 | 2023-08-17 | 2023-11-16 | 2024-03-07 | 2024-05-23
Fieldwork | SMS reminder to sample group of patients (2 days following email invitation) | 2 days following email invite | 2023-05-19 | 2023-08-18 | 2023-11-17 | 2024-03-08 | 2024-05-24
Fieldwork | Email reminder sent (7 days following email invitation) | 7 days following email invite | 2023-05-26 | 2023-08-23 | 2023-11-22 | 2024-03-13 | 2024-05-29
Fieldwork | Email/text survey links close (21 days following launch of survey) | 21 days following launch | 2023-06-09 | 2023-09-06 | 2023-12-06 | 2024-03-27 | 2024-06-12
Reporting | Survey results posted to sector secure online portal | 7 days after survey close | 2023-06-15 | 2023-09-13 | 2023-12-13 | 2024-04-03 | 2024-06-19
Reporting | Results published on Experience Explorer |  | 2023-08-31 | 2023-11-30 | 2024-02-29 | 2023-05-31 | 2024-08-30
Formulas:
Q1 August 2023 = [Q1 August 2023, row above]
Q1 August 2023 = [Q1 August 2023, row above]+13
Q2 November 2023 = [Q2 November 2023, row above]
Q2 November 2023 = [Q2 November 2023, row above]+13
Q3 February 2024 = [Q3 February 2024, row above]
Q3 February 2024 = [Q3 February 2024, row above]+1
Q4 May 2024 = [Q4 May 2024, row above]
Q4 May 2024 = [Q4 May 2024, row above]+1
Note on E6: Hanrie Le Roux: 14 July 2023 = Public Holiday - Matariki
Note on F9: Hanrie Le Roux: 23 October 2023 = Public Holiday - Labour Day

## AHS-I
| Adult hospital inpatient experience survey |  | Q4 May 2023 | Q1 August 2023 | Q2 November 2023 | Q3 February 2024 | Q4 May 2024
Phase | Process | Guide | Q4 Apr - Jun 23 | Q1 July - Sept 23 | Q2 Oct - Dec 23 | Q3 Jan - Mar 24 | Q4 Apr - Jun 24
Wave set-up | Survey sample weeks reminder | Friday before survey week | 2023-04-06 | 2023-06-30 | 2023-09-22 | 2024-01-12 | 2024-04-05
Sampling | Survey sample weeks (4 weeks): Dates of inpatients discharged from hospital | Monday-Sunday (4 weeks) | 10 April-7 May 2023 | 3 July–30 July 2023 | 25 September-22 October 2023 | 15 January-11 February 2024 | 8 April-5 May 2024
Sampling | Survey sample weeks (2 weeks): Dates of inpatients discharged from hospital | Monday-Sunday (2 weeks) | 24 April-7 May 2023 | 17 July-30 July 2023 | 9 October-22 October 2023 | 29 January-11 February 2024 | 22 April-5 May 2024
Sampling | Batch open - districts can start uploading patient sample files | Tuesday after survey sample weeks | 2023-05-09 | 2023-08-01 | 2023-10-24 | 2024-02-13 | 2024-05-07
Sampling | District patient sample file upload deadline | 6 days after batch opening 1 day before to launch of AHS-I | 2023-05-15 | 2023-08-07 | 2023-10-30 | 2024-02-19 | 2024-05-13
Fieldwork | Launch of survey: email invitation sent to sample group of patients | 7 days after batch opening 1 week before launch of APCS (to stagger the invitation process) | 2023-05-15 | 2023-08-08 | 2023-10-31 | 2024-02-20 | 2024-05-14
Fieldwork | SMS reminder & invitation sent to sample group of patients (2 days following initial email invite) | 2 days after email invite | 2023-05-17 | 2023-08-10 | 2023-11-02 | 2024-02-22 | 2024-05-16
Fieldwork | Email reminder sent (7 days following initial email invite) | 7 days after invite | 2023-05-22 | 2023-08-15 | 2023-11-07 | 2024-02-27 | 2024-05-21
Fieldwork | Email/text survey links close (21 days following launch of survey) | 21 days after launch | 2023-06-05 | 2023-08-29 | 2023-11-21 | 2024-03-12 | 2024-06-04
Reporting | Survey results posted to sector secure online portal | 7 days after deadline for paper/mail survey data | 2023-07-04 | 2023-09-26 | #REF! | 2024-04-09 | 2024-07-02
Reporting | Results published on Experience Explorer |  | 2023-08-31 | 2023-11-30 | 2024-02-29 | 2023-05-31 | 2024-08-30
Formulas:
Q2 November 2023 = [Q2 November 2023, row above]+2
Note on F3: Kania Sugandi: These dates are 2 weeks earlier than previous years in order to fit the Outpatient survey before the Christmas break.

## AHS-O
| Adult hospital outpatient experience survey |  | Q4 May 2023 | Q1 August 2023 | Q2 November 2023 | Q3 February 2024 | Q4 May 2024
Phase | Process | Guide 2-WEEK GAP FROM AHS-I | Q4 Apr - Jun 23 | Q1 July - Sept 23 | Q2 Oct - Dec 23 | Q3 Jan - Mar 24 | Q4 Apr - Jun 24
Wave set-up | Survey sample weeks reminder | Friday before survey sample weeks |  | 2023-08-11 | 2023-10-20 | 2024-02-23 | 2024-05-17
Sampling | Survey sample weeks (2 weeks): Dates of appointment | Monday-Sunday (2 weeks) | 22 May-4 June | 14 August-27 August | 6 November-19 November 2023 | 26 February-10 March | 20 May-2 June
Sampling | Batch open - districts can start uploading patient sample files | Tuesday after survey sample weeks | Tuesday 6 June | 2023-08-29 | 2023-11-21 | 2024-03-12 | 2024-06-04
Sampling | District patient sample file upload deadline | 6 days after batch opening 1 day before to launch of AHS-O | Monday 12 June | 2023-09-04 | 2023-11-27 | 2024-03-18 | 2024-06-10
Fieldwork | Launch of survey: email invitation sent to sample group of patients | 7 days after batch opening 1 day before launch of APCS (to stagger the invitation process) | 2023-06-13 | 2023-09-05 | 2023-11-28 | 2024-03-19 | 2024-06-11
Fieldwork | SMS reminder & invitation sent to sample group of patients (2 days following initial email invite) | 2 days after email invite | 2023-06-15 | 2023-09-07 | 2023-11-30 | 2024-03-21 | 2024-06-13
Fieldwork | Email reminder sent (7 days following initial email invite) | 7 days after invite | 2023-06-20 | 2023-09-12 | 2023-12-05 | 2024-03-26 | 2024-06-18
Fieldwork | Survey links close (21 days following launch of survey) | 21 days after launch | 2023-07-04 | 2023-09-26 | 2023-12-19 | 2024-04-09 | 2024-07-02
Reporting | Raw data export available in the data collection portal | 1 days after survey closes | TBC | 2023-09-27 | 2023-12-20 | 2024-04-10 | 2024-07-03
Formulas:
Q1 August 2023 = [Q1 August 2023, row above]+6
Q2 November 2023 = [Q2 November 2023, row above]+6
Q3 February 2024 = [Q3 February 2024, row above]+6
Q4 May 2024 = [Q4 May 2024, row above]+6
Note on F10: Hanrie Le Roux: Just before Christmas Break